Google Chrome Book Initiative

Project Plan

Micah Day, Dianne Iberg and Eric Weiss

Project Description

Overview

The purpose of this project is to provide Google Apps training to teachers and staff in anticipation of integrating a digital device and Google Apps into the classroom.  The project is designed to provide training to all staff in order to use Google Apps efficiently and effectively while providing a fun collaborative classroom environment for students.

Rationale

The need for an individual digital device within the classroom has arisen at the middle school.  If the pilot project goes well, the entire school (faculty and students) from there on will receive a Chrome book or some digital device that implements the Google Apps software in the classroom.  In the meantime, all district staff has an opportunity to use the Google Apps software on their desktop or other digital device for free.

Google Apps is new to almost all district staff.  Training will be needed for teachers to become proficient in all aspects of the software and have a good understanding of how cloud-based computing works.  The training is the best option for the following reasons:

- Learners can experience the software with the help of colleagues and the trainer.

- Any questions can be answered by the trainer.

- Many teachers can be taught at the same time.

- Connections can be made so teachers can implement this into the classroom.

Products

Below are charts entailing deliverables, materials, and personnel that will be used throughout the duration of the project, followed by a description of each item or person within the project and their projected outcomes?

| Deliverables | Description | Outcome(s) |
| --- | --- | --- |
| POS | Provides client(s) and project team with an understanding of the initiative or project, entailing the projects goals, objectives, success criteria, and assumptions, risks, and obstacles. | The success criteria stated within this document will be acceptable within the eyes of the client(s) and risks will be minimal. |
| RBS | Allows for the client(s) and project team to have a broad overview of the project’s tasks. | Project team will be able to expand on broader tasks. |
| Project Network Diagram | Gives the client(s) and project team an idea of how long the project will take to complete. | Entering the project, project team members will be able to generate an idea of the projects duration. |
| WBS | A more detailed document graphing the activities needed to complete the broader tasks annotated within the RBS? | Project team will be aware of all activities involved within the project. |
| Resource & Cost Analysis | Provides client(s) and project team with an estimated list of personnel facilitating the project, and materials needed to produce instruction. | Client(s) and project team will be aware of the project’s budget |
| Work Package Assignment Sheet | Allows for client(s) and project team members to view and know the dates an activity should be completed and what team member will be carrying out that task. | Will allocate for project team members to stay on top of deadlines. |
| Gant & Milestone Chart | Provides client(s) and PM the ability to manage and monitor team member’s completion of deliverables throughout the project’s life cycle. | Team members will remain on schedule with the completion of their deliverables. |

| Training Materials | Description | Outcome(s) |
| --- | --- | --- |
| Paper | Will be used for teachers and staff members to take notes | Allow for teachers and staff members to take thorough notes. |
| Google Chrome Books | Will be the technology provided by the school used to enhance their students learning. | Will be efficiently used by all teachers and staff members. |
| Job Aid (Reference Cards) | Instruction will be provided to teachers and staff members, aiding them in sequential tasks with the Chrome Books. | Teachers and staff members will be able to use the Chrome Books with minimal or no errors. |
| Instruction | The production of material created to educate the teachers and staff members. | The strategies within the instruction will impact the teachers and staff members. |
| Presentation | Teachers and staff members will be shown by a trainer how to use the Chrome Books | Teachers and staff members will know how to use the Chrome Books with 80% accuracy |
| Evaluation | Teachers and staff members will be assessed on their experience and feelings towards the Chrome Books. | At least 75% of teachers are using the Chrome Books at least 3-4 days a week. |

Equipment Installation

No software installation will be needed.

Internet connectivity will be provided by school.

Apps will be installed by teachers and staff members.

| Group/Certified Trainers | Description | Outcome(s) |
| --- | --- | --- |
| Instructional Designer | Certified designer will produce instruction stemming from the initiation and design meetings, to the creation of the projects presentation, job aids, and training. | Designer’s strategies will help the teachers and staff members learn the material presented to them within the trainer’s presentation and designed Job Aids. |
| ID Secretary | Competent secretary will aid in the management of instruction and conduct an instructional review. | Instruction will be approved by a credible source, supporting the designer’s instruction for use. |
| SME (Subject Matter Expert) | Expert will provide their expertise within the initiative and design meeting concerning the project. | Will guide the designers in the best approach to teaching and relating to the learner/user. |
| Trainer | Certified trainer will present the instruction produced by the Instructional Designer. | Trained in delivering instruction, the trainer will successfully deliver the material produced. |

Problem as to Why Initiative is Needed

Ensuring that the students are able to keep up with more advanced technologies, helping to possibly increase a student’s learning, the Google Chrome Book Initiative is being implemented to represent the idea that as technology advances, so does the student’s digital literacy within the school.  In theory, as technology evolves, so does our idea and definition of literacy.  Students need to be introduced, learn, and be capable of using various technologies and mediums with minimal difficulties.  Teaching children how to use Google Chrome Books supports a larger principle, and that is schools need to continue preparing their students, ensuring that they will have the right tools (educational experiences) to be successful within the real-world.

Approach:

The project consists of four major components, a planning stage, a development stage, presentation and evaluation.

The planning stage consists of a project initiation meeting and a design meeting.  The district administrator will need to attend the project initiation meeting with the instructional designer and subject matter expert.  This meeting will take place at the administrator’s office.  The design meeting will be between the ID and the SME and may take place either at a location convenient to both parties or virtually.

The development stage is the primary responsibility of the instructional designer and will take place at his office.  The instructional design secretary will be available at the office to perform her duties and assist the instructional designer by reviewing materials.

Presentations and evaluations will use district facilities.  Trainers will conduct two hour meetings with groups of five to fifteen teachers.  Group size is important to allow individual assistance to each teacher.

Personnel:

District administrator: The administrator will serve as liaison between the district and the project team.  The administrator’s prime duty is to provide input related to client expectations and requirements.  The administrator will also be asked to coordinate facility availability for training.

Subject matter expert: The SME will work with the instructional designer to develop guidelines for what information to include in the presentations and the sequencing of instruction to provide the most efficient and thorough training possible in the allotted time.

Instructional Designer: The designer is responsible for creating all instructional materials for presentation and distribution.

Instructional Design Secretary: The instructional design secretary will assist the designer, review materials and assign passwords for trainees.

Trainer(s): Trainers will present materials to teachers and work one on one to make teachers comfortable with using Google apps.

Please go to the next page to view the Project Plan’s charts and diagrams.

WBS

7.    Faculty Evaluation

6.        Job Aids

5.  Technical Instruction

4.  Google Videos

1. Project Manager

2. Software Training

3.    Train System Admins

1.1 Project Initiation - Initial Meeting

5.1 Feasibility Assessment

2.1 Google Drive - Creating Documents - Uploading Documents - Converting Documents - Sharing Documents

3.1 Google Dashboard

1.2 Project Plan - Scope - Task Management - Risk Management

5.2 Design Document - Design Overview - Goals & Objectives - Evaluation

3.2 Managing Users & Devices

2.2 Gmail - Composing Messages - Mail Folder - Mail Organization - Contact - User Directory - Settings

3.3 System Settings

1.3 Requirements Doc (RBS) - Software - Training - Create Instruction

4.1 https://sites.google.com/site/kahoksgafe/

6.1 Design of Job Aids

1.4 Project Network Diagram - Anticipated Timeframe - Sequence of Tasks

7.1 Interview After 2-3 Weeks

2.3 Google Calendar - User Interface - Creating Events - Sharing Calendars - Settings

2.4 Google Sites - Create Button - Online Template - Sharing & Permissions

1.6 Budget

1.5 Time Keeping

1.7 Project Control

1.8 Project Checkout

2.5 Google Apps

Project Network Diagram

Create Instruction/training for Staff

30 Days

Evaluate Faculty Participants

30 Days

Create Job Aids

7 Days

Train Teachers

18 Days

Provide Links to Google Videos

1 Day

Enhancement of IT support

5 Days

Purchasing needed materials

3 Day

Delivery of Chrome Books

14 Days

Work Package Assignment Sheet

Resource & Cost Analysis

| Total Project Cost |  |  |  | 7370 |
| --- | --- | --- | --- | --- |
| Item | Estimated Hours | Cost/hr | Total Est Cost |  |
| Project Initiation meeting | 4 |  |  | 240 |
| Instructional Designer | 4 | 40 | 160 |  |
| SME | 4 | 20 | 80 |  |
| Administrator | 4 | 0 | 0 |  |
| Design Meeting |  |  |  | 240 |
| Instructional Designer | 4 | 40 | 160 |  |
| SME | 4 | 20 | 80 |  |
| Presentation/Job Aid Design |  |  |  | 3200 |
| Instructional Designer | 80 | 40 | 3200 |  |
| Manage Software/Communications |  |  |  | 1200 |
| ID Secretary | 80 | 15 | 1200 |  |
| Instructional Review |  |  |  | 120 |
| ID Secretary | 8 | 15 | 120 |  |
| Instruction |  |  |  | 1800 |
| Trainer | 60 | 30 | 1800 |  |
| Computer Resources |  |  | 0 | 0 |
| Facilities |  |  | 0 | 0 |
| Printed Materials |  |  |  | 250 |
| Job Aids |  |  | 250 |  |
| Post Training Administration |  |  |  | 320 |
| Instructional Designer | 8 | 40 | 320 |  |
|  |  |  | 7370 | 7370 |