## QRAM V12 Rev 3
|  |  | Project: | DCMA NOSC
|  |  | Project Manager: | Scott McCall PM
|  |  | Date: | 2006-08-24
RISK IDENTIFICATION |  |  |  | PRE-MITIGATION |  |  | MITIGATION ACTIVITIES |  |  |  |  | POST MITIGATION |  |  |  | TEST
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9a) | (9b) | (9c) | (9d) | (10) | (11) | (12) | (13)
Risk ID # | Risk Type | Risk Priority | Specific Risk Item (What, Why, Impact) | Pre-Mitigation Prob of Occur | Pre-Mitigation Cost to Correct ($K) | Pre-Mitigation Cost Impact ($K) | Mitigation Activity (What, Who, When) | Mitigation Cost already in the ETC ($K) | Mitigation Cost not yet in the ETC ($K) = Delta Cost | Total Time to Execute the Mitigation | Schedule impact on the Critical Path | Post Mitigation Prob of Occur | Post Mitigation Cost to Correct ($K) | Post Mitigation Cost Impact ($K) | Date Risk can be Closed | Mitigation Effectiveness
1 | c/s/p | 2 | What: Staffing challenges to have qualified personnel in place at program start. Why: New facility in new location for this customer, steep qualifications Impact: Might have to use temporary personnel at contract start. | 20% | 5 | 1 | 1. Initiate contingency recruiting actions, i.e. Monster, Recruitmax, Salary Surveys Actionee: Program Manager ECD: 10 Sep ACD: 2. Identify current employees for TDY placement if necessary Actionee: Scott McCall ECD: 10 Sep ACD: | 1 | 0 | 20 days | 0 | 10% | 2.5 | 0.25 | 2006-09-20 | OK
2 | p | 4 | What:Identifying pool of qualified applicants with current TS clearance Why: DCMA clearance requirements are not clear. Impact: Potential to delay staffing | 25% | 5 | 1.25 | 1. Question to government asking for clarification. Actionee: Contracts ECD: 24 Aug ACD: 24 Aug 2. Execute recruiting activity. (As Above) Actionee: Project Manager ECD: As Required ACD: | 0.5 | 0 | Project Life | 0 | 15% | 25 | 3.75 | Project Closure | Reevaluate the Mitigation Effectiveness
3 | p | 3 | What: Identifying qualifed applicants with Government tool set expertise. Why: New NOSC, new location, incumbent capture may not feasible unless willing to relocate. Impact: Potential to require contractor paid for training. | 40% | 30 | 12 | 1. Identify local training sources to minimize potential costs. Actionee: Project Manager ECD: Program Life ACD: 2. Execute recruiting activity. (As Above) Actionee: Project Manager ECD: As Required ACD: | 5 | 0 | Project Life | 0 | 20% | 30 | 6 | Project Closure | OK
4 | c/p | 1 | What: Scope creep due to somewhat unbounded SOW. Why: DCMA has high expections in transition to NOSC concept. Impact: Less than optimum customer satisfaction or impact on contractual deliverables. | 25% | 10 | 2.5 | 1. Project Manager to establish frequent contact with customers and make customer relationship management an item for monthly report to government. Actionee: Program Manager ECD: Program Life ACD: | 2 | 0 | Project Life | 0 | 10% | 2.5 | 0.25 | Project Closure | OK
|  |  | Totals | 33.5% | (6): 50; (7): 16.75; MITIGATION ACTIVITIES (9b): 0; POST MITIGATION (10): 17.08%; POST MITIGATION (11): 60; POST MITIGATION (12): 10.25
|  |  | Mitigations Effectiveness ($) |  | (6): Reevaluate the Mitigation Effectiveness; MITIGATION ACTIVITIES (8): Project Reserve (PR) Amount:; POST MITIGATION (12): 10.25
[7 empty] | PR Analysis: |  | PR as a % of ETC Cost
PR as a % of SAIC ETC Cost