## Executive Report
Project State
Month | Requirements |  | RFP | Design | Construct |  | QA/UAT Testing | Closing | Closed | Approved/Pending | On-Hold | Cancelled
Aug | 9 |  | 4 | 12 | 3 |  | 3 | 6 | 2 | 57 | 3 | 1
Jul | 9 |  | 9 | 9 | 3 |  | 3 | 4 | 2 | 44 | 3 | 0
GREEN: Project is within budget, scope and on schedule. There are no major issues or risks.
YELLOW: Project has deviated slightly from the plan or there are issues and risks that put the dates, scope, and deliverables in jeopardy.
RED: Project has fallen significantly behind schedule, is forecast to be significantly over budget, or has taken on tasks that are out of scope. There are issues, and/or risks that have impacted the scope, budget, or deliverable dates.
PURPLE: Implemented into production – in Project Closure.
BLUE: Formal acceptance and approval to close obtained - project record is closed.
Completed Projects
Status | Priority | ID | Project Title | ROI | Target Go Live | Actual Go Live | Description
Closing
Status | Priority | ID | Project Title | ROI | Target Go Live | Actual Go Live | Description
Closing
Status | Priority | ID | Project Title | ROI | Target Go Live | Actual Go Live | Description
Closing
Status | Priority | ID | Project Title | ROI | Target Go Live | Actual Go Live | Description
Closing
Status | Priority | ID | Project Title | CRI | Target Go Live | Actual Go Live | Description
Closed
Status | Priority | ID | Project Title | ROI | Target Go Live | Actual Go Live | Description
Closing
Status | Priority | ID | Project Title | CRI | Target Go Live | Actual Go Live | Description
Closed
Status | Priority | ID | Project Title | ROI | Target Go Live | Actual Go Live | Description
Closing
3762 Project Title A | [7 empty] | Priority | PCR | ROI | Phase | Status
[8 empty] | 4 | 0 | 437 | Design | Yellow
Scope Summary: | [5 empty] | Status Comments:
3774 Project Title B | [7 empty] | Priority | PCR | ROI | Phase | Status
[8 empty] | 5 | 0 | 200 | Construction | Green
Summary: | [5 empty] | Status Comments:
3775 Project Title C | [7 empty] | Priority | PCR | ROI | Phase | Status
[8 empty] | 7 | 0 | -120 | Requirements | Green
Summary: . | [5 empty] | Status Comments:
3568 Project Title D | [7 empty] | Priority | PCR | ROI | Phase | Status
[8 empty] | 8 | 4 | No | QA Testing | Green
Summary: | [5 empty] | Status Comments:
3367 Project Title E | [7 empty] | Priority | PCR | ROI | Phase | Status
[8 empty] | 9 | 0 | 160 | Requirements | Green
Summary: . | [5 empty] | Status Comments:
Milestones Pending Scopte Validation
3223 Project Title | [7 empty] | Priority | PCR | CRI | Phase | Status
[8 empty] | 10 | 1 | Yes | QA Testing | Green
Summary: | [5 empty] | Status Comments:
3604 Switch Application OS Debian to RedHat | [7 empty] | Priority | PCR | CRI | Phase | Status
[8 empty] | 11 | 0 | No | Design -Phase 2 | Green
Summary: The current Switch application runs on an open-source Linux installation (Debian), an outdated, unsupported application server (JBoss), and legacy hardware (5 – Dell PE2650 servers). This project will provide a high availability, fault tolerant, mirrored environment for development and testing. | [5 empty] | Status Comments: Phase 1 deployed 8/28. Tentative Phase 2 dates pushed out: • Red Hat consultant’s timeframe for the assessment of Switch increased • Database Development hours needed
XXX | [7 empty] | Priority | PCR | CRI | Phase | Status
[8 empty] | x | 0 | No | XXXXXXX | Green
Summary: | [5 empty] | Status Comments:

## Timelines
| Current Date | 2008-10-01
Title: | Project 3762
Year | Event | Height | Axis | Label
2008-10-01 | Current Date | 7 | 39722 | Current Date
2008-08-01 | Project Kickoff | -7 | 39661 | Project Kickoff
2008-08-19 | Requirements Approved | -7 | 39679 | Requirements Approved
2008-09-26 | Design Complete | 5 | 39717 | Design Complete
2008-10-03 | Constriction Complete | -5 | 39724 | Constriction Complete
2008-10-10 | QA Testing Complete | 3 | 39731 | QA Testing Complete
2008-10-20 | Tentative Go Live | 3 | 39741 | Tentative Go Live
2008-10-30 | Project Closure | -5 | 39751 | Project Closure
Title: | Project 3774
Year | Event | Height | Axis | Label
2008-10-01 | Current Date | 7 | 39722 | Current Date
2008-08-15 | Project Kickoff | -7 | 39675 | Project Kickoff
2008-09-23 | Requirements Approved | -7 | 39714 | Requirements Approved
2008-10-02 | Design Complete |  | 39723 | Design Complete
2008-11-15 | Constriction Complete |  | 39767 | Constriction Complete
2008-12-02 | QA Testing Complete |  | 39784 | QA Testing Complete
2008-12-10 | Baselined Go Live |  | 39792 | Baselined Go Live
2008-12-25 | Project Closure |  | 39807 | Project Closure
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Title: | Project 3775
Year | Event | Height | Axis | Label
2008-10-01 | Current Date | 5 | 39722 | Current Date
2008-09-02 | Project Kickoff | -4 | 39693 | Project Kickoff
2008-09-22 | Requirements Approved | -6 | 39713 | Requirements Approved
2008-10-03 | Design Complete | 3 | 39724 | Design Complete
2008-11-10 | Constriction Complete | 5 | 39762 | Constriction Complete
2008-12-01 | QA Testing Complete | -4 | 39783 | QA Testing Complete
2008-12-11 | Baselined Go Live | 3 | 39793 | Baselined Go Live
2009-02-10 | Project Closure | 5 | 39854 | Project Closure
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Title: | Project 3568
Year | Event | Height | Axis | Label
2008-10-01 | Current Date | 5 | 39722 | Current Date
2008-06-09 | Project Kickoff | 3 | 39608 | Project Kickoff
2008-07-28 | Requirements Approved | -4 | 39657 | Requirements Approved
2008-09-16 | Design Complete | -4 | 39707 | Design Complete
2008-10-15 | Constriction Complete | -6 | 39736 | Constriction Complete
2008-10-21 | QA Testing Complete | 3 | 39742 | QA Testing Complete
2008-10-30 | Baselined Go Live | -3 | 39751 | Baselined Go Live
2008-11-18 | Project Closure | 5 | 39770 | Project Closure
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Title: | Project 3367
Year | Event | Height | Axis | Label
2008-10-01 | Current Date | 7 | 39722 | Current Date
|  | -7 | 0 | 0
|  | -7 | 0 | 0
|  | -5 | 0 | 0
|  | -7 | 0 | 0
|  | 7 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
|  | -10 | 0 | 0
Title: | Project 3223
Year | Event | Height | Axis | Label
2008-10-01 | Current Date | 5 | 39722 | Current Date
2008-05-14 | Requirements | 3 | 39582 | Requirements
2008-08-22 | Design | 3 | 39682 | Design
2008-09-29 | Construction | -3 | 39720 | Construction
2008-10-14 | QA Testing | -4 | 39735 | QA Testing
2008-10-23 | Baseline Go Live | 3 | 39744 | Baseline Go Live
2008-11-28 | Project Closure | -3 | 39780 | Project Closure
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Title: | Project 3604
Year | Event | Height | Axis | Label
2008-10-01 | Current Date | 5 | 39722 | Current Date
2008-07-10 | Design Phase 1 | 5 | 39639 | Design Phase 1
2008-07-25 | Construction Phase 1 | 3 | 39654 | Construction Phase 1
2008-08-22 | QA Phase 1 | -3 | 39682 | QA Phase 1
2008-10-31 | Design Phase 2 | 3 | 39752 | Design Phase 2
2008-12-01 | Construction Phase 2 | 1 | 39783 | Construction Phase 2
2008-12-15 | QA Phase 2 | -3 | 39797 | QA Phase 2
2008-12-24 | Project Closure | -5 | 39806 | Project Closure
2008-08-29 | Baselined Go Live Phase 1 | -5 | 39689 | Baselined Go Live Phase 1
2008-12-16 | Tentative Go Live Phase 2 | 5 | 39798 | Tentative Go Live Phase 2
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0